## Sheet1
CLIENT | PROJECT | DESIGN | DRAWING NO. | DATE ISSUED | REVISION NO. | DESIGN USE
Mainland Cicil Group | Liverpool Civic Centre Stage '2' | Hanging Stretcher Stair Scaffold | MCI-LCC-ESD0929 | 2025-09-09 | 1 | CONCEPT
Mainland Cicil Group | Liverpool Civic Centre Stage '2' | Column Demolition Scaffold | MCI-LCC-ESD0930 | 2025-10-09 | 1 | CONSTRUCTION
Richard Crooks Consrtuctions | Ivanhoe C3 Development Project | External Perimeter Scaffold | RCC-IVA-ESD0931 | 13/09/2025 | 2 | PRELIMINARY
Lend Lease Constructions | Powerhouse Parramatta Development Project | Level 5 Lift Motor Room Scaffold | LLS-PPS-ESD0932 | 15/09/2025 | 1 | CONSTRUCTION
Delta Demolition | Sydney Water, Rouse Hill, Stage 2 | Chamber Birdcage Scaffold | DEL-SWP-ESD0933 | 15/09/2025 | 1 | CONSTRUCTION
BUILT Pty Ltd | Atlassian Central Development Project | Stair 8 Birdcage Scaffold | BLT-ATL-ESD0934 | 17/09/2025 | 1 | CONSTRUCTION
Coronation | 73-78 Mary Street Development Project | South-West BLDG B Scaffold | COR-SPT-ESD0935 | 18/09/2025 | 1 | AS-BUILT
Coronation | 73-78 Mary Street Development Project | Existing Bank Scaffold | COR-SPT-ESD0936 | 2025-09-18 | 1 | AS-BUILT
Lend Lease Constructions | Watsons Bay Development Project | Main Canopy Stretcher Stair Access | LLS-WAT-ESD0937 | 2026-07-11 | 1 | CONSTRUCTION
BUILT Pty Ltd | 65 Martin Place Demolition Scaffold | External Perimeter Scaffold | BLT-MAR-ESD0938 | 2025-09-20 | 6 | CONSTRUCTION
Coronation | Erskinville Development Project | Site Shed Scaffold | COR-ERS-ESD0939 | 2025-09-24 | 1 | AS-BUILT
Lend Lease Constructions | Powerhouse Parramatta Development Project | Western Exoskeleton Craneable Loading Bay | LLS-WAT-ESD0940 | 2026-07-11 | 1 | CONSTRUCTION
Coronation | 8 Phillip Street Parramatta Development Project | Internal Lift Shaft Scaffold | COR-PHI-ESD0941 | 2025-09-27 | 1 | PRELIMINARY
ICON Constructions | Newmarket Randwick Development Project | 6.00m high Craneable Stretcher Stair Access | ICO-NEW-ESD0942 | 2025-10-03 | 1 | CONSTRUCTION
ICON Constructions | Newmarket Randwick Development Project | 6.00m high Craneable Personnel Stair Access | ICO-NEW-ESD0942 | 2025-10-03 | 1 | CONSTRUCTION
Mainland Cicil Group | Liverpool Civic Centre Stage '2' | Excavation Pitt to Ground Capping Beam Stretcher Stair Access | MCI-LCC-ESD0943 | 2025-10-03 | 1 | CONSTRUCTION
Coronation | Erskinville Development Project | Site Basement Hanging Stretcher Stair Access | COR-ERS-ESD0944 | 2025-10-09 | 1 | AS-BUILT
Lend Lease Constructions | Powerhouse Parramatta Development Project | 4.50m High Craneable Stretcher Stair Scaffold | LLS-PPS-ESD0945 | 2025-10-13 | 1 | CONSTRUCTION
Buildcorp | Dooleys Lidcombe Development Project | Internal Lift Shaft Lid Supoort Scaffold | BCP-DOL-ESD0946 | 2025-10-13 | 1 | CONSTRUCTION
McNAB | 137-147 Smithfield Development Project | Office 2 External Perimeter Scaffold | MNA-SMI-ESD0947 | 2025-10-13 | 1 | CONSTRUCTION
McNAB | 137-147 Smithfield Development Project | Office 1 External Perimeter Scaffold | MNA-SMI-ESD0948 | 2025-10-14 | 1 | CONSTRUCTION
Buildcorp | Dooleys Lidcombe Development Project | Internal Lift Shaft Lid Supoort Scaffold | BCP-DOL-ESD0949 | 2025-10-14 | 1 | CONSTRUCTION
BUILT Pty Ltd | Chiffley Square Development Project | Lift Shaft 18 Scaffold | BLT-CHF-ESD0950 | 2025-10-14 | 1 | CONSTRUCTION
Coronation | Erskinville Development Project | 7.50m Crraneable Personnel Stair Access | COR-ERS-ESD0951 | 2025-10-16 | 1 | AS-BUILT
BUILT Pty Ltd | 65 Martin Place Demolition Scaffold | External Perimeter Scaffold | BLT-MAR-ESD0952 | 2025-10-21 | 1 | CONSTRUCTION
Lend Lease Constructions | SYD067 Development Project | Internal Stair Shaft 1 Scaffold | LLS-SY6-ESD0953 | 2025-10-22 | 1 | CONSTRUCTION
BUILT Pty Ltd | Chiffley Square Development Project | Upper Ground - Level 07 PC05/PC06 Scaffold | BLT-CHF-ESD0954 | 2025-10-23 | 1 | CONSTRUCTION
BUILT Pty Ltd | 65 Martin Place Demolition Scaffold | External Perimeter Cantilevered Loading Bay Scaffold | BLT-MAR-ESD0955 | 2025-10-24 | 1 | CONSTRUCTION
Buildcorp | Powerhouse Parramatta Development Project | Internal PS1 Scaffold Works | BCO-PPS-ESD0956 | 2025-10-13 | 1 | CONSTRUCTION
Coronation | Erskinville Development Project | Baloon Advertisement Birdcage Scaffold | COR-ERS-ESD0957 | 2025-10-31 | 1 | AS-BUILT
Lend Lease Constructions | Powerhouse Parramatta Development Project | Level 6.2 Cantilevered Vent Riser Scaffold | LLS-PPS-ESD0958 | 2025-11-03 | 1 | CONSTRUCTION
Lend Lease Constructions | Powerhouse Parramatta Development Project | Internal In-Line Stretcher Stair Access Scaffold | LLS-PPS-ESD0959 | 2025-11-05 | 1 | AS-BUILT
Lend Lease Constructions | Powerhouse Parramatta Development Project | Level 04 Eastern Plantroom Catch Deck Scaffold | LLS-PPS-ESD0960 | 2025-11-05 | 1 | CONSTRUCTION
Lend Lease Constructions | Powerhouse Parramatta Development Project | Level 04 Eastern Plantroom Catch Deck Scaffold | LLS-PPS-ESD0961 | 2025-11-05 | 1 | AS-BUILT
BUILT Pty Ltd | Chiffley Square Development Project | Level 06 mezzanine 10kPa Overhead protection scaffold (01) | BLT-CHF-ESD0962 | 2025-10-23 | 1 | CONSTRUCTION
BUILT Pty Ltd | Chiffley Square Development Project | Level 06 mezzanine 10kPa Overhead protection scaffold (02) | BLT-CHF-ESD0963 | 2025-10-23 | 1 | CONSTRUCTION
BUILT Pty Ltd | 65 Martin Place Demolition Scaffold | Level 03 - 06 Perimeter Demolition Scaffold | BLT-MAR-ESD0964 | 2025-11-08 | 1 | CONSTRUCTION
Buildcorp | Powerhouse Parramatta Development Project | Level ground - Tower 1 BCA compliant stair scaffold | BCO-PPS-ESD0965 | 2025-11-10 | 1 | CONSTRUCTION
Buildcorp | Powerhouse Parramatta Development Project | Level ground - Tower 1 Stair scaffold (AT-PAC) | BCO-PPS-ESD0966 | 2025-11-10 | 1 | CONSTRUCTION
Hickory Group | 189 Kent Street Development project | Level 17 - roof 10kPa scaffold (Kwikstage) | HIC-KEN-ESD0967 | 2025-11-12 | 1 | CONCEPT DRAWING
Richard Crooks Constructions | Sydney Biomedical Accelerator development project | Basement 01/Level 01 Core wall Scaffolds | RCC-SBA-ESD0968 | 2025-11-14 | 1 | CONSTRUCTION
Lend Lease Constructions | Powerhouse Parramatta Development Project | In-Line Stretcher Stair Access (Cantilevered Landings) | LLS-PPS-ESD0969 | 2025-11-14 | 1 | AS-BUILT
ADCO Constructions | Woonona Development Project | BLDG E External perimeter scaffold | WON-ADC-ESD0970 | 2025-11-15 | 1 | CONCEPT
BUILT Pty Ltd | Atlassian Central Development Project | UGF - U/S Level 01 blockwork riser scaffold | BLT-ATL-ESD0971 | 2025-11-17 | 1 | AS-BUILT
Taylor Constructions | The Switch Development Project | Level 01 - Level 06 stretcher stair access | TAY-TSW-ESD0972 | 2025-11-17 | 1 | AS-BUILT
Taylor Constructions | The Switch Development Project | Level 06 - Level 14 stretcher stair access | TAY-TSW-ESD0973 | 2025-11-18 | 1 | AS-BUILT
BUILT Pty Ltd | Chiffley Square Development Project | Level 15 - 16 Grillage installation cantilevered scaffold | BLT-CHF-ESD0974 | 2025-11-18 | 1 | CONSTRUCTION
Lend Lease Constructions | Powerhouse Parramatta Development Project | Level 6.1 Vent Riser Scaffold Cantilever | LLS-PPS-ESD0975 | 2025-11-14 | 1 | AS-BUILT
ADCO Constructions | Woonona Development Project | BLDG A External perimeter scaffold | WON-ADC-ESD0976 | 2025-11-19 | 1 | CONCEPT
Richard Crooks Constructions | Gledswood High School Development Project | Building A external perimeter scaffold | RCC-GLD-ESD0977 | 2025-11-21 | 2 | CONSTRUCTION
BUILT Pty Ltd | Chiffley Square Development Project | PS05 beam support arrangement plan | BLT-CHF-ESD0978 | 2025-11-27 | 1 | CONSTRUCTION
BUILT Pty Ltd | EC5 Development Eastern Creen | Roof spandeck walkway bridge scaffold | BLT-EC5-ESD0979 | 2025-12-10 | 1 | CONSTRUCTION
Multiplex Constructions | Royal Far-West Manly Development Project | CCK Re-glaxing Loading Platform Scaffold | MLT-RFW-ESD0980 | 2025-12-10 | 1 | CONSTRUCTION
Richard Crooks Constructions | Gledswood High School Development Project | Building B external perimeter scaffold | RCC-GLD-ESD0981 | 2025-12-16 | 1 | CONSTRUCTION
Metropolitan Demolitions | 136-148 NSH Road Darling Point Demolition Project | External perimeter demolition scaffold | MET-NSH-ESD0982 | 2025-12-17 | 1 | CONSTRUCTION
Grange Glass & Aluminium | Randwich Childrens Hospital Development Project | Internal B1 Courtyard scaffold | GCA-RCH-ESD0983 | 2025-12-18 | 1 | CONSTRUCTION
Multiplex Constructions | Royal Far-West Manly Development Project | BKLD C level 03 falsework/edge protection scaffold | MLT-RFW-ESD0984 | 2026-01-06 | 1 | PRELIMINARY
BUILT Pty Ltd | Castle Tower Zone 2 Development Project | External stretcher stair/walkway access to carpark | BLT-CTW-ESD0985 | 2026-01-07 | 1 | PRELIMINARY
BUILT Pty Ltd | Castle Tower Zone 2 Development Project | Car bridge demolition/works scaffold | BLT-CTW-ESD0986 | 2025-01-12 | 1 | PRELIMINARY
Freecity | Frederick Street, Rockdale Development Project | External/Internal Scaffold Arrangements (Scaffold 01 - 04) | FRE-FSR-ESD0987 | 2025-01-13 | 1 | PRELIMINARY
Richard Crooks Constructions | Gledswood High School Development Project | Building C external perimeter scaffold | RCC-GLD-ESD0988 | 2026-01-14 | 2 | CONSTRUCTION
BUILT Pty Ltd | EC5 Development Eastern Creen | External covered walkway access | BLT-EC5-ESD0989 | 2026-01-17 | 1 | CONSTRUCTION
BUILT Pty Ltd | Atlassian Central Development Project | Central Station 10kPa Overhead Protection Platform | BLT-EC5-ESD0990 | 2026-01-21 | 1 | CONCEPT ONLY
BUILT Pty Ltd | Atlassian Central Development Project | Northern Atrium Birdcage Scaffold/Cantilever | BLT-EC5-ESD0991 | 2026-01-31 | 1 | PRELIMINARY
BUILT Pty Ltd | 65 Martin Place Development Project | Load Bank Relocation Scaffold | BLT-MAR-ESD0992 | 2026-02-03 | 1 | CONSTRUCTION
BUILT Pty Ltd | 65 Martin Place Development Project | Level 01 - 02 4 Tonne Rated Loading Platform | BLT-MAR-ESD0993 | 2026-02-03 | 1 | CONSTRUCTION
BUILT Pty Ltd | 65 Martin Place Demolition Scaffold | Level 01 - 02 4 Tonne Rated Loading Platform | BLT-MAR-ESD0993 | 2026-02-03 | 1 | CONSTRUCTION
BUILT Pty Ltd | EC5 Development Eastern Creek | Level Roof antenna access scaffold | BLT-EC5-ESD0994 | 2026-02-04 | 1 | CONSTRUCTION
Multiplex Constructions | Royal Far-West Manly Development Project | Level Ground - Level 03 Falsework support scaffold | MLT-RFW-ESD0995 | 2026-02-04 | 1 | CONSTRUCTION
BUILT Pty Ltd | Atlassian Central Development Project | Crown Lift shaft scaffold staging | BLT-ATL-ESD0996 | 2026-02-05 | 1 | CONCEPT ONLY
BUILT Pty Ltd | EC5 Development Eastern Creen | External walkway/stretcher stair access | BLT-EC5-ESD0997 | 2026-02-06 | 1 | CONSTRUCTION
BUILT Pty Ltd | 65 Martin Place Development Project | Chiller Structures OHP Scaffolds | BLT-MAR-ESD0998 | 2026-02-12 | 1 | PRELIMINARY
BUILT Pty Ltd | Atlassian Central Development Project | South-East loading platform scaffold (UGF - CP1) | BLT-ATL-ESD0999 | 2026-02-16 | 1 | CONSTRUCTION
Multiplex Constructions | Royal Far-West Manly Development Project | Drummond house internal birdcage scaffold | MLT-RFW-ESD1000 | 2026-02-17 | 1 | CONSTRUCTION
Richard Crooks Constructions | Sydney Biomedical Accelerator development project | Pit stretcher stair access scaffold | RCC-SBA-ESD01001 | 2026-02-19 | 1 | CONSTRUCTION
Richard Crooks Constructions | Sydney Biomedical Accelerator development project | Smaller craneable stretcher stair access | RCC-SBA-ESD1002 | 2026-02-19 | 1 | CONSTRUCTION
Richard Crooks Constructions | Sydney Biomedical Accelerator development project | 4.00m craneable stretcher stair access | RCC-SBA-ESD1003 | 2026-02-19 | 1 | CONSTRUCTION
Metropolitan Demolitions | 409 Gardeners Road, Development Project | External perimeter demolition scaffold | MET-GAR-ESD1004 | 2026-02-19 | 1 | CONSTRUCTION
Multiplex Constructions | Royal Far-West Manly Development Project | 6.00m craneable scaffold mdoule | MLT-RFW-ESD1005 | 2026-02-24 | 1 | CONSTRUCTION
Lend Lease Constructions | Watsons Bay Development Project | Building D1/D2 External Perimeter Scaffold | LLS-WAT-ESD1006 | 2026-03-05 | 1 | CONSTRUCTION
Lend Lease Constructions | Watsons Bay Development Project | Building C External Perimeter Scaffold | LLS-WAT-ESD1007 | 2026-03-05 | 1 | CONSTRUCTION
Buildcorp | 338 Botany Road, Alexandria, Development Project | EXternal perimeter scaffold | BDC-BRA-ESD1008 | 2026-03-05 | 1 | PRELIMINARY
Lend Lease Constructions | Watsons Bay Development Project | Projector installation scaffold | LLS-WAT-ESD1009 | 2026-03-06 | 1 | CONSTRUCTION
Lend Lease Constructions | Watsons Bay Development Project | Auditorium wall works scaffold | LLS-WAT-ESD1010 | 2026-03-07 | 1 | CONSTRUCTION
Icon Constructions | Blacktown Hospital Stage '2' Development | Loading platform/hoist bridge access scaffold | ICO-BLA-ESD1011 | 2026-03-10 | 1 | CONSTRUCTION
BUILT Pty Ltd | EC6 Development Eastern Creen | Internal pump room scaffold overhead protection | BLT-EC5-ESD1012 | 2026-03-11 | 1 | CONSTRUCTION
BUILT Pty Ltd | 65 Martin Place Development Project | Hoarding - Level 03 External demolition scaffold | BLT-MAR-ESD1013 | 2026-03-12 | 1 | CONSTRUCTION
BUILT Pty Ltd | Atlassian Central Development Project | Upper Ground Slip-Brick Scaffold | BLT-ATL-ESD1014 | 20/03/2026 | 1 | CONSTRUCTION
BUILT Pty Ltd | Atlassian Central Development Project | LGF - Mezzanine clay rendering scaffold | BLT-ATL-ESD1015 | 20/03/2026 | 1 | CONSTRUCTION
BUILT Pty Ltd | Chiffley Square Development Project | UGF 10kPa substation slab scaffold | BLT-ATL-ESD1016 | 23/03/2026 | 1 | CONSTRUCTION
Multiplex Constructions | Royal Far-West Manly Development Project | Building B Loading platform scaffold | MLT-RFW-ESD1017 | 25/03/2026 | 1 | CONSTRUCTION
DELTA Demolition | 65 Martin Place Development Project | Ground - Level 20 Internal Stretcher Stair Access | DEL-MAR-ESD1018 | 27/03/2026 | 1 | CONSTRUCTION
DELTA Demolition | 65 Martin Place Development Project | Level 09-10 Slab Demolition Catch-deck scaffold | DEL-MAR-ESD1019 | 28/03/2026 | 1 | CONSTRUCTION
Richard Crooks Constructions | Sydney Biomedical Accelerator development project | External pit accessway scaffold | RCC-SBA-ESD1020 | 30/03/2026 | 1 | AS-BUILT
BUILT Pty Ltd | 90 Victoria Road, Bellevue Hill development project | Inetrnal/external beam trolley scaffold | BLT-VRB-ESD1021 | 30/03/2026 | 1 | CONSTRUCTION
BUILT Pty Ltd | 113 Hollinswoth Road, Marsden Park, Development Project | Internal lift shaft lid support scaffolds | BLT-CDC-ESD1022 | 31/03/2026 | 1 | CONSTRUCTION
BUILT Pty Ltd | 65 Martin Place Development Project | Internal Ground floor lobby bridcage scaffold | BLT-MAR-ESD1023 | 2026-01-04 | 1 | CONSTRUCTION
Richard Crooks Constructions | Sydney Biomedical Accelerator development project | External accessway bridge scaffold | RCC-SBA-ESD1024 | 2026-02-04 | 1 | CONCEPTUAL
Richard Crooks Constructions | Leppington High School Development Project | BLDG D External Stretcher Stair Access | RCC-LEP-ESD1025 | 2026-02-04 | 1 | CONSTRUCTION
BUILT Pty Ltd | Castle Tower Zone 2 Development Project | External 2T (Tonne) Rated loading platform | BLT-CTW-ESD1026 | 2026-08-04 | 1 | CONSTRUCTION
BUILT Pty Ltd | 113 Hollinswoth Road, Marsden Park, Development Project | External Edge-Protection Scaffold | BLT-CDC-ESD1027 | 2026-10-04 | 1 | CONSTRUCTION
Coronation | 881-885 Bourke Street, Waterloo NSW, Development | Parcel 1 - External Perimeter Scaffold | BLT-CDC-ESD1028 | 14/04/2026 | 1 | PRELIMINARY
Coronation | 881-885 Bourke Street, Waterloo NSW, Development | Parcel 2 - External Perimeter Scaffold | BLT-CDC-ESD1029 | 14/04/2026 | 1 | PRELIMINARY
Coronation | 881-885 Bourke Street, Waterloo NSW, Development | Parcel 3- External Perimeter Scaffold | BLT-CDC-ESD1030 | 14/04/2026 | 1 | PRELIMINARY
Coronation | 881-885 Bourke Street, Waterloo NSW, Development | Parcel 4 - External Perimeter Scaffold | BLT-CDC-ESD1031 | 14/04/2026 | 1 | PRELIMINARY
BUILT Pty Ltd | Chiffley Square Development Project | GF/UGF Internal Scaffold Arrangement | BLT-CHF-ESD1032 | 15/04/2026 | 1 | AS-BUILT
BUILT Pty Ltd | Chiffley Square Development Project | Level 13-14 Eastern Cantilevered Scaffold | BLT-CHF-ESD1033 | 16/04/2026 | 1 | AS-BUILT
BUILT Pty Ltd | Atlassian Central Development Project | UGF Northern Atrium Works Scaffold | BLT-ATL-ESD1034 | 16/04/2026 | 1 | CONSTRICTION
Metropolitan Demolitions | ST-George Hospital Demolition Project | External perimeter demolition scaffold | MET-SGH-ESD1035 | 17/04/2026 | 1 | CONSTRUCTION
BUILT Pty Ltd | 113 Hollinswoth Road, Marsden Park, Development Project | Craneable Personnel Stair Access Scaffold | BLT-CDC-ESD1036 | 21/04/2026 | 1 | CONSTRUCTION
BUILT Pty Ltd | 113 Hollinswoth Road, Marsden Park, Development Project | 1.00m External Edge Protection Scaffold | BLT-CDC-ESD1037 | 22/04/2026 | 1 | CONSTRUCTION
BUILT Pty Ltd | 113 Hollinswoth Road, Marsden Park, Development Project | External Lattice Beam Handrail Scaffold | BLT-CDC-ESD1038 | 22/04/2026 | 1 | CONSTRUCTION
BUILT Pty Ltd | 90 Victoria Road, Bellevue Hill development project | Inetrnal/external beam trolley scaffold | BLT-VRB-ESD1039 | 30/04/2026 | 1 | CONSTRUCTION
Lend Lease Constructions | Blue-Tounge Data Centre Development | Internal lift shaft scaffold 001 | LLC-PBT-ESD1040 | 30/04/2026 | 1 | CONSTRUCTION
Lend Lease Constructions | Blue-Tounge Data Centre Development | Internal lift shaft scaffold 002 | LLC-PBT-ESD1041 | 30/04/2026 | 1 | CONSTRUCTION
Lend Lease Constructions | Blue-Tounge Data Centre Development | Internal lift shaft scaffold 003 | LLC-PBT-ESD1042 | 30/04/2026 | 1 | CONSTRUCTION
Lend Lease Constructions | Blue-Tounge Data Centre Development | Internal lift shaft scaffold 004 | LLC-PBT-ESD1043 | 30/04/2026 | 1 | CONSTRUCTION
Lend Lease Constructions | Blue-Tounge Data Centre Development | Internal lift shaft scaffold 005 | LLC-PBT-ESD1044 | 30/04/2026 | 1 | CONSTRUCTION
Lend Lease Constructions | Blue-Tounge Data Centre Development | Internal lift shaft scaffold 006 | LLC-PBT-ESD1045 | 30/04/2026 | 1 | CONSTRUCTION
Lend Lease Constructions | Blue-Tounge Data Centre Development | Internal lift shaft scaffold 007 | LLC-PBT-ESD1046 | 30/04/2026 | 1 | CONSTRUCTION
Hickory Group | 189 Kent Street Development project | Internal Confined Space Slab Support Scaffold | HIC-KEN-ESD1047 | 2026-06-05 | 1 | CONSTRUCTION
BUILT Pty Ltd | Castle Tower Zone 2 Development Project | External Loading Dock Wall Scaffold | BLT-CTW-ESD1048 | 2026-07-05 | 1 | CONSTRUCTION
Richard Crooks Consrtuctions | Ivanhoe C3 Development Project | North-Western Scaffold Arrangement | RCC-IVA-ESD1049 | 2026-09-05 | 1 | AS-BUILT
BUILT Pty Ltd | Chiffley Square Development Project | Internal Shaft hoist Grillage Scaffold | BLT-CHF-ESD1050 | 2026-11-05 | 1 | CONSTRUCTION
BUILT Pty Ltd | 65 Martin Place Development Project | Souther Level 07 - Level 10 Demolition Scaffold | BLT-MAR-ESD1051 | 15/05/2026 | 1 | CONSTRUCTION
Metropolitan Demolitions | Bankstown Tafe Demolition Project | External Perimeter Demolition Scaffold | MET-BTA-ESD1052 | 16/05/2026 | 1 | CONSTRUCTION
Richard Crooks Consrtuctions | Parramatta Riverside Theatre Project | Internal Works Scaffold | RCC-PRT-ESD1053 | 19/05/2026 | 1 | CONCEPT
BUILT Pty Ltd | EC6 Development Eastern Creek | EC6 Plant Deck Personnel Stair Access | BLT-EC6-ESD1054 | 19/05/2026 | 1 | CONSTRUCTION
BUILT Pty Ltd | Chiffley Square Development Project | Brent Street Lobby 10kPa OHP Scaffold | BLT-CHF-ESD1055 | 20/05/2026 | 1 | CONSTRUCTION
Icon Constructions | Blacktown Hospital Stage '2' Development | Level 04 Mechanical Penetartion support scaffold | ICO-BLA-ESD1056 | 22/05/2026 | 1 | CONSTRUCTION
SH Constructions | Herman Residence Development, Rouse Hill | Building A External Perimeter Scaffold | SHC-HER-ESD1057 | 23/05/2026 | 1 | CONSTRUCTION
BUILT Pty Ltd | Castle Tower Zone 2 Development Project | Birdge Demolition/Remediation Scaffold - FRONT FACE | BLT-CTW-ESD1058 | 26/05/2026 | 1 | CONCEPT ONLY
BUILT Pty Ltd | Castle Tower Zone 2 Development Project | Birdge Demolition/Remediation Scaffold - REAR FACE | BLT-CTW-ESD1059 | 26/05/2026 | 1 | CONCEPT ONLY
BUILT Pty Ltd | EC4 Development Eastern Creen | Duct Handrail scaffold (Lower) | BLT-EC4-ESD1060 | 28/05/2026 | 1 | CONSTRUCTION
BUILT Pty Ltd | EC5 Development Eastern Creen | Duct Handrail scaffold (Upper) | BLT-EC4-ESD1061 | 28/05/2026 | 1 | CONSTRUCTION
Lend Lease Constructions | Powerhouse Parramatta Development Project | Roof Rope-Guiding Scaffold | LLS-PPS-ESD1062 | 2026-02-06 | 1 | PRELIMINARY
BUILT Pty Ltd | Chiffley Square Development Project | Existing hoading top-up for Swing Stage Access | BLT-CHF-ESD1063 | 2026-09-06 | 1 | CONSTRUCTION
H&R Hassarati | 189 Kent Street Development project | Neighbouring Building Cantilevered Demolition Scaffold | HRH-KTS-ESD1064 | 2026-09-06 | 1 | CONSTRUCTION
BUILT Pty Ltd | EC5 Development Eastern Creen | Overhead Site Shed Works Scaffold - Design 1 | BLT-EC5-ESD1065 | 2026-10-06 | 1 | CONSTRUCTION
BUILT Pty Ltd | EC5 Development Eastern Creen | Overhead Site Shed Works Scaffold - Design 2 | BLT-EC5-ESD1066 | 2026-10-06 | 1 | CONSTRUCTION
BUILT Pty Ltd | 65 Martin Place Development Project | Internal Lift Shafts 1 - 7 Internal Scaffold Works | BLT-MAR-ESD1067 | 17/06/2026 | 1 | CONSTRUCTION
BUILT Pty Ltd | Chiffley Square Development Project | Level 05 10kPa OHP Walkway Scaffold | BLT-CHF-ESD1068 | 20/05/2026 | 1 | CONSTRUCTION
BUILT Pty Ltd | Chiffley Square Development Project | Basement 01 10kPa OHP Walkway Scaffold | BLT-CHF-ESD1069 | 20/05/2026 | 1 | CONSTRUCTION
BUILT Pty Ltd | 113 Hollinswoth Road, Marsden Park, Development Project | Internal Doorway access 10kPa Scaffold | BLT-CDC-ESD1070 | 22/06/2026 | 1 | CONSTRUCTION
Multiplex Constructions | Royal Far-West Manly Development Project | Lift Shaft 002 External Extents Scaffold | MLT-RFW-ESD1071 | 22/06/2026 | 1 | CONSTRUCTION
Lend Lease Constructions | Watsons Bay Development Project | Building C Cantilevered Scaffold Elevation | LLS-WAT-ESD1072 | 23/06/2026 | 1 | CONSTRUCTION
Lend Lease Constructions | Watsons Bay Development Project | Building C Hoist Access Scaffold | LLS-WAT-ESD1073 | 26/06/2026 | 1 | CONSTRUCTION
BUILT Pty Ltd | Atlassian Central Development Project | South-East Corner Clay Rendering Scaffold | BLT-ATL-ESD1074 | 27/06/2026 | 1 | CONSTRUCTION
BUILT Pty Ltd | Chiffley Square Development Project | Level 06 Cladding Installation Scaffold | BLT-CHF-ESD1075 | 2026-01-07 | 1 | CONSTRUCTION
Lend Lease Constructions | Powerhouse Parramatta Development Project | External rubbish chute scaffold | LLS-PPS-ESD1076 | 2026-01-07 | 1 | AS-BULT
Lend Lease Constructions | Watsons Bay Development Project | Craneable mobile scaffold bay | LLS-WAT-ESD1077 | 2026-02-07 | 1 | CONSTRUCTION
BUILT Pty Ltd | 65 Martin Place Development Project | Internal shaft 17-18 Demolition Scaffold | BLT-MAR-ESD1078 | 2026-06-07 | 1 | CONSTRUCTION
BUILT Pty Ltd | 65 Martin Place Development Project | Internal shaft 16 Demolition Scaffold | BLT-MAR-ESD1079 | 2026-06-07 | 1 | CONSTRUCTION
BUILT Pty Ltd | 113 Hollinswoth Road, Marsden Park, Development Project | Zone 'H' Generator Overhead Protection Scaffold | BLT-CDC-ESD1080 | 2026-07-07 | 1 | CONSTRUCTION
Cash McInnes Projects | St Luke's High School Refurbishment Project | External Perimeter Refurbishment Project | CMP-SLH-ESD1081 | 2026-08-07 | 1 | CONSTRUCTION
BUILT Pty Ltd | Chiffley Square Development Project | Electrical Box Overhead Protection Scaffold | BLT-CHF-ESD1082 | 2026-10-07 | 1 | CONSTRUCTION